## Slide 1: Evolution plan for Invest4All
DRAF
Sara Nodehi | Joost Visser | 2 November 2021
This evolution plan was created as an synthetic case for testing the evolution planning methodology and supporting materials.

## Slide 2: Executive Summary
    Current state: Invest4All is an investment banking application for mid-income private individuals and families in The Netherlands, allowing lost-cost and low-risk investment into the AEX stock market. Invest4All currently has 4,000 users.
    Invest4All is currently available as web application with support from all major browsers. On the server-side the system runs on a group of servers hosted in-house.
    Invest4All is currently not profitable.
    Opportunity: Low and even negative interest rates on savings accounts has increased interest among private individuals and families in investment banking. This rise in interest occurs in The Netherlands, but also in other European countries. Current (Dutch) users of Invest4All have strong interest in investing not only in the AEX, but in exchanges worldwide.
    Ambition: Make Invest4All available to users across the European Union, allowing them to invest in all major European exchanges. Let the number of users grow from 4,000 now, to 100,000 in three years.
    Steps: (1) Enable connection to more exchanges, (2) Increase scalability in terms of number of users and number of transaction, (3) Support internationalisation.

## Slide 3: Situation
    Invest4All is an investment banking application for mid-income private individuals and families in The Netherlands, allowing lost-cost and low-risk investment in the AEX stock market and related funds.
    Functionalities: Users can inspect the current status of their investments, make changes to specific investments, adapt their investment strategy, and obtain a multi-year projection of the value of their investments.
    Users: Invest4All currently has 4,000 users. About 65% of these users checks the status of their investments each month. About 10% of these users make a change to their investments or their investment strategy each month.
    Software profile: Invest4All is currently available as web application with support from all major browsers. On the server-side the system runs on a group of servers hosted in-house. The client-side is programmed in Angular and the server-side is programmed in C#. The total code base has a rebuild value of 50 person-years. The quality of the code base is above market average. The development team works according to Agile-Scrum, uses a modern development environment, and has fully automated integration, testing, and deployment.
    Supervision: The application is regularly audited, and audit reports are shared with the Dutch and European national banks and the Dutch financial markets authority (AFM).
    Continued on next slide

## Slide 4: Situation
    Problems: The system has experienced brief moments of unavailability as a result of peak loads occurring at the end of each working day.
    Investment4All currently runs at a loss. Operation and maintenance of Invest4All is currently €65,000 per month. Revenue from subscriptions and transaction fees amounts to €60,000 per month.

## Slide 5: Ambition
    Make Invest4All available to users across the European Union, allowing them to invest in all major European exchanges. Let the number of users grow from 4,000 now, to 100,000 in three years.
Ambition |  | 
Goal | Stakeholder interest | Motivation
What to achieve in 12-18 months? | Who benefits and how? | Which strength is used to seize which opportunity? Which weakness is remediated to mitigate which threat?
Increase user based and associated revenue to achieve at least a 40% profit. | CFO | The current user base is restricted to the Dutch market but can be expanded to other European countries.
Ensure stability, also under high peak loads. | COO | Current in-house deployment is not scalable. High-quality code and development process allow re-deployment on cloud infrastructure.
Increase user satisfaction by widening investment possibilities. | Customers | Current limitation to Dutch exchange can be removed to give users access to broad investment possibilities.

## Slide 6: Gap analysis
Gaps |  |  |  | 
What is the name of the gap? | What is the area of the gap? | What are you now? | What would you like to be? | What are the possible or alternative ways to solve the gaps?
Lack of availability | Performance gap | Application is sometimes unavailable during peak load | 100% availability, also under peak loads | Make the application scale better
Low number of users | Market gap | 4,000 users | 100,000 users | Roll out to more countries
Not profitable | Profit gap | €5,000 loss per month | at least €500,000 profit per month | Increase revenue (at least 10-fold) more than costs (at most 3-fold)
Current state
Ambition state
Possible solution directions
Current State
Type of the gap
Gap

## Slide 7: Design moves
Design move |  |  |  |  | 
What is the name of the design move? | What benefit are you trying to achieve? What is the marked effect or influence of this design move? | What is the measure of success? | What changes need to be made to the software? What other actions need to be taken? | What are the costs, in terms of effort, required expertise, prerequisites that need to be fulfilled? | What risks need to be controlled to assure a successful outcome?
Cloud deployment | Ensure scalability | Automatic scaling under increased load | (1) Migrate server-side code to Azure, (2) Configure auto-scaling, (3) Test and audit | 6 person-month initial effort, then cloud operation expense of €2 per user per month | Current dev team has no cloud experience
Extensible architecture | Allow fast connection of new exchanges | New exchange can be added without changing existing code | (1) Isolate AEX-specific code, (2) Create exhange configuration interface, (3) Support AEX through configuration, not code | 6 person-months development effort | Errors may be introduced by code changes. Code base becomes more complex.
(Continued) |  |  |  |  | 
Risks
[What could go wrong?]
Cost
Actions
Criteria of done output
Strategic intent outcome
Design Moves

## Slide 8: Design moves
Design Moves |  |  |  |  | 
Design move | Strategic intent outcome | Criteria of done output | Actions | Cost | 
What is the name of the design move? | What benefit are you trying to achieve? What is the marked effect or influence of this design move? | What is the measure of success? | What changes need to be made to the software? What other actions need to be taken? | What are the costs, in terms of effort, required expertise, prerequisites that need to be fulfilled? | What risks need to be controlled to assure a successful outcome?
Add exchanges | Add new exchanges for large markets | German, French, Italian, Spanish, Belgian exhanges are connected | (1) Configure each exchange (2) Take into operation | 1 person-months configuration effort per exchange | APIs of various exchanges may not work as documented.
Internationalisation | Make the application accesible to non-Dutch users | Users from all EU countries are using the application. | (1) Support multiple languages, (2) Support multiple identification mechanisms | 6 person-months development effort | Development team is not proficient in the supported languages
Risks
[What could go wrong?]

## Slide 9: Benefit generation for stakeholders
9
Action/ Design move | Responsible stakeholder | Benefiting stakeholder |  | 
By which design moves or in which step in the roadmap the benefit gets created? | Which stakeholder is responsible for this benefit generation? | Which stakeholder is benefiting from the benefit generation? | What is the short term goal? What immediate benefit is? | What is the long term benefit?
Internationalisation | CTO, COO | CFO | None. | Invest4All will become profitable
Cloud deployment | CTO, COO | User | Always available | Always available
Add exchanges | CTO, COO | User | More investment possibilities | Better spread, better yield
… |  |  |  | 
Benefits
Immediate benefit
Long term benefit

## Slide 10: Risk assessment
Risks |  |  |  |  |  | 
What is the risk ID? | What is the name of the risk? | During which design move might this risk occur? | What is the description of the risk? | If a risk occurs and is not mitigated, what is the impact of the most likely problem that will occur? | What is the state of being probable or chance of a threat occurring? | What is the level of the risk?
1 | Cloud skills | Cloud deployment | The current dev team has no cloud experience | Major | Likely | Extreme
2 | New errors (Bugs) | Extensible architecture | Code changes may introduce errors. | Major | Possible | High
3 | Code complexity | Extensible architecture | Code base becomes more complex by code changes. | Major | Possible | High
4 | Poor API documentation | Add exchanges | APIs of various exchanges may not work as documented. | Major | Likely | Extreme
5 | Lack of proficiency in supported languages | Internationalisation | The development team is not proficient in the supported languages | Moderate | Possible | High
Risk
Related design move
Risk Description
Risk Impact
Risk Likelihood
Risk Level
Risk ID

## Slide 11: Mitigation actions
Mitigation actions |  |  |  |  | 
Which risk ID? | What is the name of the risk? | What are the actions to reduce or eliminate the risk? | What is the risk impact after risk mitigation? | What is the risk likelihood after risk mitigation? | What is the risk level after risk mitigation?
1 | Cloud skills | 1) Use the support of a third-party certified by the target cloud provider to assess the required needs for pinpointing in-house skills gaps 2) Hire additional personnel to fill the identified gaps | Moderate | Possible | High
2 | New errors (Bugs) | High code coverage (Make sure that code coverage is 100% or more) | Minor | Possible | Moderate
3 | Code complexity | 100% code coverage+ Use error prediction tooling such as Rollbar and CircleCI to identify which code changes caused errors automatically | Moderate | Possible | High
4 | Poor API documentation | 1) Reduce reliance on the documentation and test API beforehand 2) Use CloudRail and connect up to any cloud service or device while coding. | Minor | Possible | Moderate
5 | Lack of proficiency in supported languages | Put somebody in charge and get an external service such as TMS (Translation Management System) to check whether you are doing localization right or not. | Minor | Possible | Moderate
Risk
Mitigation Actions
Revised-Risk Impact
Revised-Risk Likelihood
Revised-Risk Level
Risk ID

## Slide 12: Risk mitigation matrix
Certain
Moderate
High
Extereme
Extereme
Extereme
Likely
Moderate
High
High
Extereme
Extereme
Possible
Low
Moderate
High
High
Extereme
Unlikely
Low
Moderate
Moderate
High
High
Rare
Low
Low
Low
Moderate
Moderate
Likelihood
Impact
Insignificant
Minor
Moderate
Major
Catastrophic
Risk ID
Effect of risk mitigation
4
4
2
2
1
1
5
5
3
3

## Slide 13
Add exchanges
Extensible architecture
Cloud deployment
2 months
Quarter 2
Quarter 3
Quarter 4
Internationalisation
January
February
March
April
May
Migrate to Azure
Configure auto scaling
Auto scaling
Isolate AEX-specific code
Isolate AEX-specific code
Support AEX through configuration, not code
Configure each exchange
Take into operation
Support multiple languages
Support multiple identification mechanisms
Developer 1 & 2
Developer 1 & 2
Developer 1 & 2
Developer 3
Developer 3
Developer 1, 2 & 3
Developer 4
Developer 1
Developer 1
Developer 2, 3 & 4

## Slide 14: Monitoring and evaluating the plan
Migrate server-side code to Azure
Configure auto-scaling
Test and audit
Move the system from on-premise to cloud computing
Ensure scalability
Fast connection of new exchanges
Automatic scaling under increased load
Employ required staff
Approve the organizational cloud readiness
A created cloud roadmap
Decrease of mean time to repair or mean time between failures (time)
Increase in the speed and reliability of the service
Increase in customer and employee satisfaction
Time to bring new users
Time to bring new services to market
Reducing the hours that the system is unavailable
The system never gets overloaded
Budget availability
Time availability
Employee availability
Infrastructures availability
Clear agenda
Good leadership
Protection of expertise and assets
Clear agenda
On schedule progress
Good leadership
Success in roadmaking
Review the progress
Good leadership
Workplace cooperation
Goal/
Ambition state
Outcomes
Outputs
Actions/
Design moves
Project Summary
Indicators
Dependent on
Use checkmarks to show the answer of following questions in the indicators column during the execution:
Have you achieved your overall goal and targets?
Which outcomes have already been achieved?
Which outputs have already been achieved?
Which actions have already been executed?

## Slide 15: Appendices

## Slide 16
Stakeholder analysis
Who are your stakeholders or stakeholder group? | What are the impacts of stakeholders on a business? | How supportive of the project objectives the stakeholder is? | What are the reasons for resistance or support? | What are the actions to address this stakeholder group?
Customers (Audience) | Affected | Supportive | To have access to broad investment possibilities. | Removing the current limitations in Dutch exchange.
Dutch European national bank (Promoter) | Impactful | Supportive | Increase the number of users and expand the market | Make the system available to the other European countries.
Dutch Authority for the Financial Markets (AFM) (Promoter) | Decision authority | Supportive | Increase the number of users and expand the market | Make the system available to the other European countries.
Chief Financial Officer (CFO)(Latent) | Decision authority | Resistant | The CFO wants to increase profitability while reducing costs. Implementing design moves will be costly initially, and therefore, it is hard for the CFO to make this change. | The IT team should work with the CFO to justify why they need to change the current situation of the application and what the result is in the long term.
Chief Operating Officer (COO) (Promoter) | Impactful | Supportive | The COO of the companies brings the right company cultures to the organizations. And help the companies run smoothly. | During the planning phase, the COO should be invited to advise and communicate the changes across the company and identify the required skills and training.
Chief Technical Officer (CTO) (Promoter) | Decision authority | Supportive | These people are aware of potential problems regarding the technology within the organization; they can guide the IT team to undertake necessary actions to implement new changes. | These people should be invited from the beginning to the planning sessions, and their opinions need to be collected.
Stakeholders
Impact Level
Support Level
Reasons
Actions
Stakeholders

## Slide 17: SWOT analysis
Strengths | Weaknesses
What does the system do well? What unique capabilities does the system have? The quality of the code base is above the market average (High-quality code) Audition of application is being done regularly. The system uses a modern development environment that provides fully automated integration, testing, and deployment. The strong interest of both Dutch and non-Dutch users to use the application. | What could be improved? What capabilities are lacking? Unavailability of application as a result of peak loads occurring at the end of each working day. Current in-house deployment is not scalable Users only have access to Dutch exchange.
Opportunities | Threats
How else could the system be used? What emerging demand could the system satisfy? Interest of Dutch users to invest in exchanges worldwide. Interest of non-Dutch users to use the application | How could the system fail? What damage could the system do? Investment4All currently runs at a loss Users might use competitors' systems that provide accessibility to broad investment possibilities.

## Slide 18: TOWS analysis
 | Weaknesses | Strengths
Threats | Counter weaknesses and threats: How can you minimize the system’s weaknesses to avoid identified threats? | Leverage strengths to minimize threats: How can you use the system’s strengths to minimize the identified threats?
 | The current limitation to Dutch exchange can be removed to give users access to broad investment possibilities and prevent users from going to competitors. | Cloud deployment to ensure stability, also under high peak loads.
Opportunities | Counter weaknesses through exploiting opportunities: What actions can you take to minimize the system’s weaknesses using the identified opportunities? | Leverage strengths to maximize opportunities: Which of the system’s strengths can be used to maximize the identified opportunities?
 | Make Invest4All available to users across the European Union to increase user-based and associated revenue to achieve at least a 40% profit. | Make Invest4All available to users across the European Union and give users access to broad investment possibilities to increase user satisfaction.